## Sprint Backlog
ID | Type | Actor | Feature | Story/Task | Acceptance Criteria | Priority | Sprint | Status
Lira-01 | User Story | Librarian | Admin Login | As a librarian, I want to log in to the system using my administrative credentials so that I can securely access the catalog dashboard and analytics tools. | - Given the librarian is on the login screen, when they click 'Login with APC Account', then they are redirected to the Microsoft sign-in page. - Given the librarian enters valid administrative credentials, when authentication succeeds, then the system recognizes their role and redirects them to the admin dashboard. - Given the authentication fails, then they are shown an error message and denied access. | High | 1 | To Do
Lira-02 | User Story | Librarian | Manage Library Catalog | As a librarian, I want to add, edit, or delete library resources in the catalog dashboard so that the repository remains updated and synchronized with Koha ILS. | - Given the librarian is logged in with admin privileges, when they submit new resource metadata, then the system validates and commits it to the Koha ILS database. - Given the record is committed, when the catalog updates, then the AI Processing Service immediately indexes it. - Given Koha ILS synchronization fails or metadata is invalid, then the system saves changes locally in a queue and alerts the librarian. | Medium | 1 | To Do
Lira-03 | User Story | Librarian | Manage Book Loans | As a librarian, I want to process book checkouts and returns so that the system accurately tracks physical asset borrowing and triggers overdue alerts. | - Given a patron presents a book, when the librarian scans the ID and barcode, then the system updates the book's status to 'Borrowed' in Koha ILS. - Given a patron has reached their maximum borrowing limit, when the librarian attempts a checkout, then the system rejects the transaction. - Given a due date passes, when the system monitors loan durations, then it triggers an automated overdue notification. | Medium |  | To Do
Lira-04 | User Story | Librarian | Manage Chatbot | As a librarian, I want to configure the AI chatbot's operational parameters so that its tone, rules, and knowledge sources meet institutional standards. | - Given the librarian adjusts chatbot settings, when they deploy to the sandbox, then they can test the configuration. - Given the configuration is valid, when they deploy to production, then the chatbot updates its operational parameters. - Given there is an invalid parameter configuration, when the librarian attempts deployment, then the system prevents it. - Given there is insufficient chat data for FAQ suggestions, then the system prompts for manual FAQ creation. | Medium |  | To Do
Lira-05 | User Story | Librarian | Manage Reports | As a librarian, I want to generate operational analytics reports so that I can monitor catalog searches, loan frequencies, and chatbot utilization. | - Given the librarian is on the Analytics dashboard, when they select metrics and a timeframe, then the system compiles visualizations. - Given the report is generated, when the librarian selects export, then they can download it as a PDF or CSV. - Given the requested date range contains no data, then the system displays an empty-state message. | Low |  | To Do
Lira-06 | User Story | Student/Faculty | User Login | As a user, I want to log in to the system so that I can securely access my personalized educational tools and materials. | - Given the user is on the login screen, when they click 'Login with APC Account', then they are redirected to the Microsoft sign-in page. - Given the user enters valid credentials, when authentication succeeds, then they land on their personalized dashboard. - Given authentication fails, then the user sees Microsoft's error message. - Given the user is already signed into Microsoft (SSO), when they access the login page, then they are automatically authenticated. | High | 1 | To Do
Lira-07 | User Story | Student/Faculty | View Library Catalog | As a user, I want to search and browse the library catalog so that I can find available resources. | - Given the user is on the catalog page, when they enter keywords, then the system queries Koha and displays matching items. - Given no matching records are found, then the system displays a 'No materials found' message and suggests broader terms. - Given the user selects an item, then the system renders the complete catalog record. | High | 1 | To Do
Lira-08 | User Story | Student/Faculty | AI Chatbot (Book Recommendations) | As a user, I want to receive personalized book recommendations through the AI chatbot so that I can discover relevant study materials. | - Given the user opens the chatbot, when they request study materials, then the system displays a curated list of recommendations. - Given the chatbot analyzes recent reading history, when a recommendation is provided, the AI generates contextually relevant suggestions. - Given the user interacts with a recommendation, then the system updates their profile to refine future generations. | Medium |  | To Do
Lira-09 | User Story | Student/Faculty | AI Chatbot (Core/FAQ) | As a user, I want to ask general library questions in the chatbot so that I can instantly receive AI-generated FAQ answers. | - Given the chat window is active, when the user types a question, then the system routes the query to the AI and generates a relevant FAQ answer. - Given the user has previous chatbot interactions, then the system displays their conversation history. - Given the AI Service times out, then the system displays a graceful fallback message. - Given the query is inappropriate, then the system generates a courteous refusal response. | High |  | To Do
Lira-10 | User Story | Student/Faculty | AI Chatbot (E-book Summaries) | As a user, I want the chatbot to generate e-book summaries so that I can quickly review the core concepts of reading materials. | - Given the user is viewing an e-book, when they click 'Generate Summary', then the system sends a request to the AI. - Given the AI finishes processing, then it generates a concise, accurate summary and displays it in the chat. | Medium |  | To Do
Lira-11 | User Story | Student/Faculty | AI Chatbot (E-book Citations) | As a user, I want to use the chatbot to format e-book citations so that I can easily copy properly formatted references. | - Given the user is viewing an e-book, when they select 'Cite this Book', then the system prompts the AI to build the citation. - Given the AI extracts metadata, then it generates a correctly formatted citation string. - Given source metadata is incomplete for a citation, then the system prompts the user to manually input missing fields. | High |  | To Do
Lira-12 | User Story | Student/Faculty | Borrow Books & Track Active Loans | As a user, I want to initiate a borrow request for an available physical book so that I can secure it for pickup. | - Given the user searches the catalog, when they click the 'Borrow' button on an available book, then the system validates their borrowing status. - Given the user confirms the details, then the system records the loan request in Koha and updates the item availability. - Given the user has reached their borrowing limit, then the system denies the request. - Given the item is no longer available, then the system notifies the user and suggests similar items. | Medium |  | To Do
Lira-13 | User Story | Student/Faculty | Borrow Books & Track Active Loans | As a user, I want to view my active loans and due dates on a dashboard so that I return books on time. | - Given the user accesses their dashboard, then the system retrieves active loans from Koha ILS and displays a list of borrowed items and due dates. - Given a book is nearing its due date, when the user checks their dashboard, then the system highlights the upcoming deadline. - Given Koha ILS is unreachable, when the user accesses the dashboard, then the system displays an error message. | Medium |  | To Do