## User Stories
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | State | Type | Project | Sprint | Story Points | Effort | Owner | Status | Remarks.1
Lira-01 | Admin Login (Koha) | Librarian | log in to the Koha system using my staff credentials | I can securely access the Koha catalog management and circulation modules. | Given the librarian is on the Koha login screen, when they enter valid staff credentials and submit, then Koha authenticates them and redirects to the staff interface. Given the authentication fails, then Koha displays an error message and denies access.
Lira-02 | Manage Library Catalog | Librarian | add (create) a new catalog item via the management dashboard | I can ensure new inventory is searchable in the system | Given the Librarian successfully signs in to Koha, and the Librarian accesses the dashboard, When they submit valid new item details, Then the system updates the catalog database and displays a success confirmation message.
Lira-03 | Manage Library Catalog | Librarian | view (read) the current catalog list and item details | I can monitor and verify the existing library inventory | Given the Librarian successfully signs in to Koha, and the Librarian accesses the catalog management dashboard, When the dashboard loads, Then the system displays the current catalog list.
Lira-04 | Manage Library Catalog | Librarian | edit (update) existing catalog item details | I can keep the library records accurate | Given the Librarian successfully signs in to Koha, and the Librarian edits an item, When they submit updated details, Then the system validates and saves the changes. Given the Librarian submits item details, When data validation fails (e.g., missing ISBN), Then the system highlights errors and prompts for correction.
Lira-05 | Manage Library Catalog | Librarian | remove (delete) a catalog item from the database | I can ensure discarded or lost books are no longer searchable | Given the Librarian successfully signs in to Koha, and the Librarian selects a catalog item, When they confirm the deletion, Then the system removes the record. Given the Librarian modifies/deletes an item, When the item is currently checked out, Then the system invokes the borrowed books process to resolve status conflicts.
Lira-06 | User Login | Student/Faculty | sign in to the LIRA platform using my APC Microsoft 365 account | I can securely access personalized LIRA features like My List and semantic search. | Given the user is on the LIRA login screen, when they select 'Login with APC Account', then they are redirected to the Microsoft sign-in page. Given valid institutional authentication, when Microsoft returns a successful response, then LIRA establishes the user session and links it to the user's application profile. Given authentication fails, then access to personalized features is denied and an appropriate error is shown.
Lira-07 | View Library Catalog | Student/Faculty | search the library catalog using criteria such as title, author, or keyword | I can easily find required resources | Given the student/faculty successfully signs in to the LIRA system, and the user accesses the catalog search interface, When they enter search criteria, Then the system retrieves matching database records and displays a list of matching catalog items. Given the user searches the catalog, When no items match the search criteria, Then the system displays a "No results found" message.
Lira-08 | View Library Catalog | Student/Faculty | select a specific item from the search results | I can view detailed information, including availability and location | Given the student/faculty successfully signs in to the LIRA system, and the user views a list of matching catalog items, When they select a specific item, Then the system displays detailed information for the selected item, including availability and location.
Lira-09 | Manage Borrowed Books | Librarian | record (create) a new borrowing transaction via the central ILS (Koha) | the inventory lifecycle checkout is successfully tracked | Given the Librarian successfully signs in to Koha, and a user successfully checks out a book, When the transaction needs recording, Then the system automatically commits the new checkout log to Koha.
Lira-10 | Manage Borrowed Books | Librarian | view (read) the synchronized circulation status of library materials | I can have oversight of circulating inventory | Given the Librarian successfully signs in to Koha, and the Librarian opens the LIRA interface, When the local system queries Koha, Then it displays the synchronized status of borrowed books.
Lira-11 | Manage Borrowed Books | Librarian | update an existing borrowing record (e.g., check-in, renew) | the central ILS maintains an accurate, up-to-date state | Given the Librarian successfully signs in to Koha, and a return or renewal is initiated, When the transaction log is committed in Koha, Then the LIRA system validates and updates the local interface. Given a transaction needs updating, When the Koha system is unreachable, Then the system queues the transaction and alerts the Librarian.
Lira-12 | Manage Borrowed Books | Librarian | resolve or mark a borrowed record as lost (delete/remove from active circulation) | inaccurate or unrecoverable inventory is no longer tracked as active | Given the Librarian successfully signs in to Koha, and a catalog management override is required for a lost book, When the Librarian flags it, Then the system marks the borrowed record as resolved/lost and removes it from active circulation.
Lira-13 | Borrow Books | Student/Faculty | initiate a borrow request for a selected, available item | I can successfully acquire a book | Given the student/faculty successfully signs in to the LIRA system, and the user has a valid account and initiates a borrow request, When they confirm the request and accept terms, Then the system updates the item status to 'Checked Out' and displays a borrowing confirmation receipt and due date. Given the user initiates a borrow request, When the user has a blocked account or overdue items, Then the system denies the borrow request and displays a warning. Given the borrow process is ongoing, When the item becomes unavailable during the transaction, Then the system cancels the process and notifies the user.
Lira-14 | Ask AI Chatbot | Student/Faculty | type and submit a question into the chat widget | I can get immediate research assistance | Given the student/faculty successfully signs in to the LIRA system, and the user types a question into the chat widget, When they submit the query, Then the system routes the query, formats the retrieved answer, and displays it in the interface. Given the user submits a query, When the AI engine cannot understand the query, Then the system displays a fallback message asking the user to rephrase. Given the user submits a query, When the AI service times out, Then the system apologizes and provides contact info for a human librarian.
Lira-15 | Admin Login (LIRA Chatbot) | Librarian | log in to the LIRA system using my administrative credentials | I can securely access the LIRA admin dashboard to manage the chatbot and analytics tools. | Given the librarian is on the login screen, when they click 'Login with APC Account', then they are redirected to the Microsoft sign-in page. Given the librarian enters valid administrative credentials, when authentication succeeds, then the system recognizes their admin role and redirects them to the admin dashboard. Given the authentication fails, then they are shown an error message and denied access.
Lira-16 | Manage Chatbot | Librarian | upload (create) new knowledge sources or custom prompts in the configuration panel | the AI expands its knowledge base and capabilities | Given the Librarian successfully signs in to the LIRA system with admin privileges, and the Librarian accesses the Chatbot configuration panel, When they upload a new knowledge document, Then the system applies the new source to the AI engine. Given the Librarian uploads a document, When it is incompatible, Then the system rejects it and shows an error message.
Lira-17 | Manage Chatbot | Librarian | view (read) the current chatbot configuration and interaction logs | I can audit the AI's settings and user interactions | Given the Librarian successfully signs in to the LIRA system with admin privileges, and the Librarian navigates to the Chatbot management area, When the configuration panel opens, Then the system displays current parameters and prompt logs for analytics.
Lira-18 | Manage Chatbot | Librarian | edit (update) existing knowledge sources or chatbot parameters | the AI's responses remain accurate and safe | Given the Librarian successfully signs in to the LIRA system with admin privileges, and the Librarian edits the configuration panel, When they save the changes, Then the system validates and applies the updated settings to the AI engine.
Lira-19 | Manage Chatbot | Librarian | remove (delete) outdated knowledge sources or prompts | the AI does not provide obsolete or incorrect information | Given the Librarian successfully signs in to the LIRA system with admin privileges, and the Librarian views knowledge sources, When they choose to delete an obsolete document, Then the system removes it and the AI ceases to use it for context.
Lira-20 | Manage Reports | Librarian | generate (create) a new statistical or operational report | I can compile new data on library usage and chatbot interactions | Given the Librarian successfully signs in to Koha, and the Librarian selects a report type and date range, When data is retrieved from LIRA and Koha, Then the system aggregates the combined data. Given a report is generated, When Koha is offline, Then the system generates a partial report with a warning note.
Lira-21 | Manage Reports | Librarian | preview and download (read) generated reports | I can view the compiled data or export it for external stakeholders | Given the Librarian successfully signs in to Koha, and the system has aggregated the data, When processing is complete, Then it displays a report preview on the dashboard and provides a downloadable file (PDF/Excel).
Lira-22 | Manage Reports | Librarian | adjust parameters of an active report view (update) | I can refine the scope of my analytics | Given the Librarian successfully signs in to Koha, and the Librarian is viewing a report preview, When they update the date range or report type, Then the system re-aggregates the data to reflect the new parameters. Given the date range is updated, When the range contains no data, Then the system outputs an empty report with a notification.
Lira-23 | Manage Reports | Librarian | clear or delete an old report from the dashboard view | my workspace remains uncluttered | Given the Librarian successfully signs in to Koha, and a report is actively displayed, When the Librarian dismisses or clears the report, Then the system removes the preview data from the dashboard.